## Project Schedule Template
Transportation Alternatives Project Schedule
NOMINATING ENTITY:
PROJECT NAME:
TASK | Responsible Entity | FY 2025 | [9 empty] | FY 2026 | [11 empty] | FY 2027 | [11 empty] | FY 2028 | [11 empty] | FY '26 TA SET-ASIDE FUNDS LAPSE
|  | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG
PROJECT INITIATION | bar: FY 2025 NOV to FY 2025 JUL
Project Selection (Approval by TPB) | TPB | bar: FY 2025 DEC
Deadline to Add Project to EPMPO TIP (November 2024) | LG | bar: FY 2025 FEB
Anticipated STIP Approval | - | bar: FY 2025 NOV to FY 2025 APR
Local Government Risk Assessment | LG/TxDOT | bar: FY 2025 JAN to FY 2025 MAR
Execute Project Agreement | LG/TxDOT | bar: FY 2025 NOV to FY 2025 MAY
State Letter of Authority for Engineering | TxDOT | bar: FY 2025 JUN
Project Kick-Off Meeting with TxDOT | LG/TxDOT | bar: FY 2025 JUL
DESIGN (Only Necessary if Design is Not Complete)
Submit Schematics | LG
Submit 60% Plans for Review | LG
Submit 90% Plans for Review | LG
Submit 100% Plans for Review | LG
PS&E Approval | TxDOT
ENVIRONMENTAL COMPLIANCE
Complete TxDOT's Scope Development Tool (Recommended) | LG
Resource Agency Review | TxDOT
Environmental Approval | TxDOT
UTILITIES | LG
Relocate Incidental Franchise Utilities
CONSTRUCTION
Letter of Authority (FPAA and SLOA) | TxDOT
Open Bid | LG/TxDOT
Award Construction Contract (TxDOT Concurrence if LG Let) | LG/TxDOT
Final Inspection & Acceptance of Construction Project | LG/TxDOT
Notes: * All dates listed above are estimates only and are subject to change
◊ = Milestone dates
LG = Local Government
The deadline for agencies to submit TA Set-Aside projects into the TIP is February 2025.
Agencies are responsible for initiating project coordination and agreements with TxDOT.
The approval of the STIP is anticipated to be April 2021. All work prior to STIP approval is shaded gray and not eligible for reimbursement.
To obligate funds for construction, the opening of bids must occur before the end of the State's fiscal year (August).
An unrealistic project schedule requiring a TIP modification adds four to five months, potentially causing TA Set-Aside funds to lapse.
All bicycle/pedestrian projects require some degree of environmental compliance documentation. Approximately six months will be necessary for the TxDOT District to process and clear this phase.
Environmental compliance phase work can only be completed after Design.
Right of Way and Utilities are not eligible activities for TA Set-Aside funds.
Additional project tasks or milestones can be added to the project schedule if applicable.